## Framework Template
# | Phase | Task | Description | Owner | Depends On | Status | Evidence / Notes | Delta vs Original POA
PHASE 0: SPECIFICATIONS
F-01 | 0 | VaNi Product Framework PRD v2 | Complete architecture, skill system, VDF, recipes, multi-tenancy, tech stack | Claude.ai | - | Done | VaNi-Product-Framework-v2.docx delivered | —
F-02 | 0 | POA documents | Master tracking spreadsheet + handoff narrative | Claude.ai | - | Done | VaNi-POA-Master.xlsx + VaNi-POA-Handoff.docx | —
F-03 | 0 | TypeScript interfaces | shared/types/ — Tenant, Skill, SkillContext, Recipe, VaniConfig, VDFComponent | Claude.ai | F-01 | Done | shared/types.ts exists in KI-Prime repo with SkillContext, SkillDb, QueryResult | Was "Not Started" — built during organic dev
F-04 | 0 | Base DB migrations | Framework tables: tenants, users, conversations, memory, logs. RLS policies. | Claude.ai | F-01 | Done | vn_ prefixed tables running in Supabase. RLS disabled for debugging. | Was "Not Started" — built organically
F-05 | 0 | Docker Compose template | docker-compose.yml with API, vLLM, Postgres, Redis services | Claude.ai | F-01 | Partial | Redis+BullMQ connected. vLLM mocked (VANI_MOCK=true). No formal docker-compose.yml yet. | Was "Not Started"
F-06 | 0 | vani.config.ts template | Product config interface with vaniMode, tenancy, tiers, channels, themes | Claude.ai | F-03 | Done | vani.config.ts exists in KI-Prime with vaniMode, tenancy, system prompt, tiers | Was "Not Started"
PHASE 1: FRAMEWORK SKELETON (Built organically in VaNiBase)
F-07 | 1 | Monorepo scaffolding | npm init, tsconfig, eslint, directory structure | Claude Code | F-01..06 | Done | VaNiBase repo on GitHub (kamalcharan/VaNiBase). KI-Prime uses as submodule. | Was "Not Started"
F-08 | 1 | API server setup | Express.js + TypeScript, health check, error handling, env config | Claude Code | F-07 | Done | /health, /metrics, /health/ready all working. Full middleware pipeline. | Was "Not Started"
F-09 | 1 | JWT auth middleware | Verify JWT, extract tenant_id, user_id, tier. Supabase JWT. | Claude Code | F-08 | Done | JWT auth + dev bypass via X-Dev-Tenant-Id / X-Dev-User-Id headers | Was "Not Started"
F-10 | 1 | Tenant context builder | Load tenant profile, entity context, filter skill catalog by tier. | Claude Code | F-09 | Done | framework/context-builder/build-context.ts. set_tenant_context() has pooler issue (see bugs). | Was "Not Started"
F-11 | 1 | Skill executor | Parse tool calls, inject tenant_id, run functions, return results + recipe | Claude Code | F-10 | Done (bugs) | framework/skill-executor/executor.ts works. BUG: success field undefined, log write fails. | Was "Not Started" — built but has 2 critical bugs
F-12 | 1 | Skill registry | Scan skills/ dir, build catalog from SKILL.md, tier filtering | Claude Code | F-11 | Done | shared/skill-registry.ts discovers skills, imports handlers, registers with framework | Was "Not Started"
F-13 | 1 | VaNi engine client | HTTP client for vLLM. 3 modes: full/explain/off. | Claude Code | F-10,F-11 | Partial | VANI_MOCK=true for dev. Real LFM2 integration not tested. Mock mode works. | Was "Not Started"
F-14 | 1 | Escalation service | Claude API client for complex reasoning. | Claude Code | F-13 | Not Started | No escalation path built yet | —
F-15 | 1 | Memory store | pgvector conversation memory. Store/retrieve by tenant+entity. | Claude Code | F-08 | Not Started | vn_conversations table exists but pgvector semantic search not implemented | —
F-16 | 1 | Base migrations runner | Run framework SQL on startup. Idempotent. | Claude Code | F-04 | Done | Migrations run. Tables created in Supabase. | Was "Not Started"
PHASE 2: SHELL + VDF COMPONENTS
F-17 | 2 | Next.js app scaffold | App router, layout, theme provider, sidebar, header. 6 themes. | Claude Code | F-07 | Done | Next.js shell renders all 9 recipe pages in sidebar. VDF components present. | Was "Not Started"
F-18 | 2 | Recipe renderer engine | Read recipe JSON, look up components, render dynamic page. | Claude Code | F-17 | Partial | 9 recipes loaded via /api/v1/recipes. Shell pages show empty — data fetching not wired. | Was "Not Started" — recipes load but don't render data
F-19 | 2 | Component: kpi-card | Label, value, trend, status. 4 variants. | Claude Code | F-18 | Done | Part of 19 VDF components built | Was "Not Started"
F-20 | 2 | Component: data-table | Sortable columns, pagination, row click. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-21 | 2 | Component: doughnut-chart | Chart.js doughnut with legend. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-22 | 2 | Component: line-chart | Chart.js line, multi-series, time axis. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-23 | 2 | Component: bar-chart | Chart.js bar, horizontal + vertical. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-24 | 2 | Component: probability-gauge | Custom SVG arc gauge 0-100. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-25 | 2 | Component: sparkline | Inline mini trend. Custom SVG. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-26 | 2 | Component: timeline | Chronological event list. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-27 | 2 | Component: stat-row | Horizontal row of labeled stats. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-28 | 2 | Component: badge | Status indicator. 4 variants. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-29 | 2 | Component: slider-panel | What-if slider with live recalc. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-30 | 2 | Component: action-bar | Row of action buttons. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-31 | 2 | Component: filter-row | Dropdowns, search, toggle filters. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-32 | 2 | Component: wizard | Multi-step form with validation. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-33 | 2 | Component: approval-card | Agent proposal Accept/Modify/Reject. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-34 | 2 | Component: insight-card | VaNi proactive insight. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-35 | 2 | Component: briefing-panel | Stacked insight cards for daily digest. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-36 | 2 | Component: suggestion | VaNi recommendation + confidence. | Claude Code | F-18 | Done | Part of 19 VDF components | Was "Not Started"
F-37 | 2 | Component: chat-panel | Slide-in VaNi chat. Message list + input. | Claude Code | F-13 | Done | Part of 19 VDF components. Not wired to API yet. | Was "Not Started" — component exists, API wiring pending
F-38 | 2 | Theme engine | 6 themes. Light/dark. CSS vars. | Claude Code | F-17 | Done | 6 themes carried from KI-Prime prototype | Was "Not Started"
F-39 | 2 | Layout: dashboard-3row | 3-row grid layout template. | Claude Code | F-18 | Done | Layout templates present in shell | Was "Not Started"
F-40 | 2 | Layout: detail-sidebar | Main content + right sidebar. | Claude Code | F-18 | Done | Layout templates present | Was "Not Started"
F-41 | 2 | Layout: list-detail | Left list + right detail. | Claude Code | F-18 | Done | Layout templates present | Was "Not Started"
F-42 | 2 | Layout: briefing | Stacked cards for VaNi home. | Claude Code | F-18 | Done | Layout templates present | Was "Not Started"
PHASE 3: INFRA + DEPLOYMENT
F-43 | 3 | Dockerfile.api | Node.js API container. Multi-stage. | Claude Code | F-08 | Not Started |  | —
F-44 | 3 | Dockerfile.shell | Next.js shell container. | Claude Code | F-17 | Not Started |  | —
F-45 | 3 | Dockerfile.vani | vLLM inference server with LFM2. | Claude Code | - | Not Started |  | —
F-46 | 3 | docker-compose.yml | Full stack compose. Dev + prod profiles. | Claude Code | F-05 | Not Started |  | —
F-47 | 3 | BullMQ setup | Redis job queue for async + scheduled. | Claude Code | F-15 | Partial | Redis+BullMQ connected and operational. No scheduled jobs configured yet. | Was "Not Started"
F-48 | 3 | Monitoring setup | Prometheus metrics + Grafana. | Claude Code | F-43..47 | Partial | /metrics endpoint exists. No Grafana dashboard. | Was "Not Started"
F-49 | 3 | README + skill authoring guide | How to create a new product. | Claude Code | All | Not Started |  | —
BUGS: CRITICAL FIXES (New — not in original POA)
BUG-01 | Bug | Fix success field in executor.ts | result.success is undefined → NOT NULL violation in vn_skill_execution_log | Claude Code | F-11 | Bug | Set result.success = true/false before writing log | NEW task from organic build
BUG-02 | Bug | Fix toPositional regex | Regex matches LIMIT 1 as param. Use /(?::¦\$)([a-zA-Z]\w*)/g | Claude Code | F-11 | Bug | framework/db/pool.ts | NEW task from organic build
BUG-03 | Bug | Nuclear ki_ prefix replace | portfolio-skill inline SQL missing ki_ prefix | Claude Code | - | Bug | Run replace script on skills/portfolio-skill/functions/*.ts | NEW task from organic build
BUG-04 | Bug | planning_math export fix | planning-math.ts needs named export | Claude Code | - | Bug | Non-critical but blocks planning-skill | NEW task from organic build

## KI-Prime
# | Phase | Task | Description | Owner | Depends On | Status | Evidence / Notes | Delta vs Original POA
PHASE 0: SPECIFICATIONS
KI-01 | 0 | vani.config.ts | Product config: vaniMode=full, tenancy=operator, entity=client | Claude.ai | - | Done | vani.config.ts in KI-Prime repo | Was "Not Started"
KI-02 | 0 | portfolio-skill SKILL.md | 5 functions: get_holdings, get_allocation, calc_xirr, get_portfolio_summary, compare_holdings | Claude.ai | KI-01 | Done | SKILL.md exists. 4 handlers built. | Was "Not Started"
KI-03 | 0 | planning-skill SKILL.md | 5 functions: get_goals, calc_goal_gap, project_goal, suggest_sip_increase, create_goal | Claude.ai | KI-01 | Done | SKILL.md exists. 5 handlers built. planning_math export bug. | Was "Not Started"
KI-04 | 0 | market-skill SKILL.md | 5 functions: get_nav, get_nav_history, compare_schemes, get_category_performance, search_schemes | Claude.ai | KI-01 | Done | SKILL.md exists. 5 handlers built. | Was "Not Started"
KI-05 | 0 | client-skill SKILL.md | 5 functions: get_clients, get_client_profile, get_risk_profile, update_client, get_family_group | Claude.ai | KI-01 | Done | SKILL.md exists. 3 handlers built. get_clients VERIFIED with real data. | Was "Not Started"
KI-06 | 0 | alert-skill SKILL.md | 5 functions: get_alerts, check_rebalance, check_sip_health, check_tax_harvest, generate_daily_briefing | Claude.ai | KI-01 | Partial | Spec only. No handlers built. | Was "Not Started" — spec exists
KI-07 | 0 | report-skill SKILL.md | 4 functions: generate_portfolio_report, generate_goal_report, generate_capital_gains, generate_review_deck | Claude.ai | KI-01 | Partial | Spec only. No handlers built. | Was "Not Started" — spec exists
KI-08 | 0 | comms-skill SKILL.md | 4 functions: send_portfolio_update, send_goal_reminder, send_market_update, schedule_review | Claude.ai | KI-01 | Partial | Spec only. No handlers built. | Was "Not Started" — spec exists
KI-09 | 0 | import-skill SKILL.md | 4 functions: import_investwell, import_cas, import_nse_transactions, reconcile_holdings | Claude.ai | KI-01 | Done | SKILL.md exists. 4 handlers built. | Was "Not Started"
KI-10 | 0 | Recipe: daily-briefing.json | Layout: briefing. Insight cards + quick actions + chat. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-11 | 0 | Recipe: portfolio-view.json | Layout: dashboard-3row. KPIs + doughnut + holdings table. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-12 | 0 | Recipe: client-360.json | Layout: detail-sidebar. Profile + holdings + goals + risk. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-13 | 0 | Recipe: goal-dashboard.json | Layout: dashboard-3row. Goal KPIs + probability + SIP slider. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-14 | 0 | Recipe: goal-deep-dive.json | Layout: detail-sidebar. Projection + what-if + suggestion. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-15 | 0 | Recipe: scheme-explorer.json | Layout: list-detail. Search + NAV chart + comparison. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-16 | 0 | Recipe: client-list.json | Layout: list-detail. Client list + search/filter + summary. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-17 | 0 | Recipe: planning-playground.json | Layout: dashboard-3row. Multi-scenario sliders. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-18 | 0 | Recipe: plan-vs-reality.json | Layout: comparison. Target vs actual + drift. | Claude.ai | KI-01 | Done | Loaded in recipe registry | Was "Not Started"
KI-19 | 0 | DB migrations | Tables: clients, portfolios, holdings, transactions, goals, schemes, nav_history. RLS. | Claude.ai | KI-01 | Done | ki_ prefixed tables in Supabase. RLS disabled. | Was "Not Started"
KI-20 | 0 | Tier config | Starter ₹499, Professional ₹1499, Enterprise ₹3999. | Claude.ai | KI-01 | Done | tiers.config.ts exists | Was "Not Started"
KI-21 | 0 | Claude Code handoff doc | File-by-file build instructions, acceptance criteria. | Claude.ai | KI-01..20 | Done | CLAUDE-CODE-HANDOFF.md + CLAUDE.md in both repos | Was "Not Started"
PHASE 1: CORE SKILLS (Built organically)
KI-22 | 1 | GitHub repo from template | Create ki-prime/ from template. Copy overlay. | Manual | F-All | Done | kamalcharan/KI-Prime on GitHub. VaNiBase as submodule. | Was "Not Started"
KI-23 | 1 | Supabase project setup | Create ki-prime-supabase. Auth + connection strings. | Manual | KI-22 | Done | Project ref: oghpfkyxujiojflohnnd. Mumbai region pooler. | Was "Not Started"
KI-24 | 1 | Raw PG setup | Provision PostgreSQL. Run migrations. | Manual | KI-22 | Done | Using Supabase PG via transaction pooler port 6543 | Was "Not Started"
KI-25 | 1 | portfolio-skill functions | get-holdings, get-allocation, calc-xirr, get-portfolio-summary. Unit tests. | Claude Code | KI-02,F-11 | Partial | 4 handlers built. BUG: inline SQL missing ki_ prefix. Not tested live. | Was "Not Started" — built but has prefix bug
KI-26 | 1 | portfolio-skill SQL queries | holdings-by-client.sql, allocation-breakdown.sql. All with $tenant_id. | Claude Code | KI-25 | Partial | SQL exists but ki_ prefix missing in inline SQL | Was "Not Started"
KI-27 | 1 | client-skill functions | get-clients, get-client-profile, get-risk-profile. Unit tests. | Claude Code | KI-05 | Done | 3 handlers built. get_clients VERIFIED returning 5 clients with real data. | Was "Not Started" — VERIFIED working
KI-28 | 1 | market-skill functions | get-nav (MFAPI), get-nav-history, search-schemes, compare-schemes. | Claude Code | KI-04 | Partial | 5 handlers built. Not tested live. | Was "Not Started"
KI-29 | 1 | planning-skill functions | get-goals, calc-goal-gap, project-goal, suggest-sip-increase. | Claude Code | KI-03 | Partial | 5 handlers built. planning_math export bug. Not tested live. | Was "Not Started"
KI-30 | 1 | import-skill functions | import-investwell (CSV), import-cas (PDF). Reconciliation. | Claude Code | KI-09 | Partial | 4 handlers built. Not tested live. | Was "Not Started"
KI-31 | 1 | End-to-end test: skill loop | User question → VaNi → skill → data. Verify tenant isolation. | Claude Code | KI-25..30 | Partial | client-skill verified e2e. Other skills untested. | Was "Not Started"
SEED DATA (New — not in original POA)
KI-SD1 | Seed | Demo tenant + user | 1 tenant (Demo Distributor), 1 user (dev@vani.local) | Claude Code | - | Done | In Supabase | NEW
KI-SD2 | Seed | Sample clients | 5 clients: Priya Mehta, Vikram Desai, Anita Joshi, Rajesh Kumar, Sunita Agarwal | Claude Code | - | Done | With AUM, SIP counts, goals, risk profiles | NEW
KI-SD3 | Seed | Sample market data | 8 schemes, 40 NAV records, 17 holdings, 6 transactions, 8 goals | Claude Code | - | Done | In Supabase | NEW
PHASE 2: SHELL + RECIPES
KI-32 | 2 | Wire recipe renderer to API | Shell fetches skill result + recipe from API, renders page. | Claude Code | F-18,KI-31 | Not Started | Shell pages show empty — data fetching not wired | —
KI-33 | 2 | Render: daily-briefing | VaNi home with insight cards, quick actions. | Claude Code | KI-10 | Not Started |  | —
KI-34 | 2 | Render: client-list | Searchable client list with AUM badges. | Claude Code | KI-16 | Not Started |  | —
KI-35 | 2 | Render: client-360 | Client profile + holdings + goals + risk. | Claude Code | KI-12 | Not Started |  | —
KI-36 | 2 | Render: portfolio-view | Holdings table + allocation doughnut + KPIs. | Claude Code | KI-11 | Not Started |  | —
KI-37 | 2 | Render: goal-dashboard | Goal KPIs + probability chart + SIP slider. | Claude Code | KI-13 | Not Started |  | —
KI-38 | 2 | Render: scheme-explorer | Scheme search + NAV history + comparison. | Claude Code | KI-15 | Not Started |  | —
KI-39 | 2 | VaNi chat panel wiring | Slide-in chat connected to API. | Claude Code | F-37 | Not Started |  | —
KI-40 | 2 | Auth flow | Supabase Auth login → JWT → daily-briefing. | Claude Code | F-09 | Not Started |  | —
KI-41 | 2 | Settings screen | Profile, theme, preferences. | Claude Code | F-17 | Not Started |  | —
PHASE 3: INTELLIGENCE + CHANNELS
KI-42 | 3 | alert-skill functions | get-alerts, check-rebalance, check-sip-health, check-tax-harvest, generate-daily-briefing. | Claude Code | KI-06 | Not Started |  | —
KI-43 | 3 | Daily briefing cron | BullMQ scheduled job per tenant. | Claude Code | KI-42,F-47 | Not Started |  | —
KI-44 | 3 | report-skill functions | PDF generation. Portfolio, goal, capital gains reports. | Claude Code | KI-07 | Not Started |  | —
KI-45 | 3 | Render: goal-deep-dive | Single goal projection + what-if + suggestion. | Claude Code | KI-14 | Not Started |  | —
KI-46 | 3 | Render: planning-playground | Multi-scenario comparison with sliders. | Claude Code | KI-17 | Not Started |  | —
KI-47 | 3 | Render: plan-vs-reality | Target vs actual allocation + drift. | Claude Code | KI-18 | Not Started |  | —
KI-48 | 3 | Claude API escalation | Complex reasoning → Claude Sonnet. | Claude Code | F-14 | Not Started |  | —
KI-49 | 3 | comms-skill + WhatsApp | WhatsApp Business API integration. | Claude Code | KI-08 | Not Started |  | —
KI-50 | 3 | Subscription tier enforcement | Middleware: tier check, skill filter, rate limit. | Claude Code | KI-20 | Not Started |  | —
KI-51 | 3 | Security audit | Prompt injection, RLS verification, JWT. | Manual | All | Not Started |  | —
KI-52 | 3 | Load test | 500 concurrent distributors. | Manual | All | Not Started |  | —

## KaalaDristi
# | Phase | Task | Description | Owner | Depends On | Status | Evidence / Notes | Delta vs Original POA
PHASE 0: SPECIFICATIONS + DATA PIPELINE
KD-01 | 0 | vani.config.ts | vaniMode=explain, tenancy=subscriber, entity=market/index | Claude.ai | - | Not Started | Repo exists (kamalcharan/kaala-dristi) but not on VaNi framework yet | —
KD-02 | 0 | risk-score-skill SKILL.md | 3 functions: get_risk_today, get_risk_by_date, get_risk_breakdown | Claude.ai | KD-01 | Not Started |  | —
KD-03 | 0 | calendar-skill SKILL.md | 3 functions: get_calendar_7day, get_calendar_30day, get_calendar_range | Claude.ai | KD-01 | Not Started |  | —
KD-04 | 0 | planetary-skill SKILL.md | 3 functions: get_positions_today, get_aspects_today, get_events_upcoming | Claude.ai | KD-01 | Not Started |  | —
KD-05 | 0 | market-data-skill SKILL.md | 3 functions: get_market_today, get_market_history, get_correlation | Claude.ai | KD-01 | Not Started |  | —
KD-06 | 0 | explanation-skill SKILL.md | 2 functions: explain_risk, explain_regime | Claude.ai | KD-01 | Not Started |  | —
KD-07 | 0 | Recipe: risk-dashboard.json | Risk gauge + regime + 7-day strip + explanation | Claude.ai | KD-01 | Not Started |  | —
KD-08 | 0 | Recipe: calendar-view.json | 30-day calendar grid with color-coded risk | Claude.ai | KD-01 | Not Started |  | —
KD-09 | 0 | Recipe: historical-overlay.json | Dual-axis: risk score + market price | Claude.ai | KD-01 | Not Started |  | —
KD-10 | 0 | DB migrations | planetary_positions, aspects, events, moon_intraday, risk_scores, market_daily | Claude.ai | KD-01 | Partial | Existing repo has partial schema. Needs alignment with VaNi framework conventions. | Was "Not Started"
KD-11 | 0 | Tier config | Free, Pro ₹299/mo, Institutional API | Claude.ai | KD-01 | Not Started |  | —
KD-12 | 0 | Ephemeris pipeline spec | pyswisseph → planetary_positions + aspects + events. 40yr. | Claude.ai | KD-01 | Partial | Ephemeris data generated per memory. Python pipeline partial. | Was "Not Started"
KD-13 | 0 | Risk calculation spec | Weighted scoring → daily_risk_scores | Claude.ai | KD-01 | Not Started |  | —
KD-14 | 0 | Market data pipeline spec | yfinance → NIFTY + BANKNIFTY | Claude.ai | KD-01 | Not Started |  | —
KD-15 | 0 | Claude Code handoff doc | Build instructions for KaalaDristi | Claude.ai | KD-01..14 | Not Started |  | —
PHASE 1: DATA PIPELINE (Parallel to framework)
KD-16 | 1 | Supabase project setup | Create kaaladristi-supabase. Auth + connections. | Manual | KD-01 | Not Started |  | —
KD-17 | 1 | Run migrations | Create all tables from migration spec. | Claude Code | KD-10 | Not Started |  | —
KD-18 | 1 | Ephemeris generator | pyswisseph → planetary_positions. 40yr ~135K rows. | Claude Code | KD-12,KD-17 | Partial | Ephemeris data generated (per memory). Not loaded into Supabase framework tables. | Was "Not Started"
KD-19 | 1 | Aspect calculator | Positions → aspects between DC pairs | Claude Code | KD-18 | Not Started |  | —
KD-20 | 1 | Event extractor | Retrograde stations, nakshatra changes, gandanta | Claude Code | KD-18 | Not Started |  | —
KD-21 | 1 | Moon intraday generator | Moon at 4 market times per day | Claude Code | KD-18 | Not Started |  | —
KD-22 | 1 | Risk score calculator | All astro → weighted composite → daily_risk_scores | Claude Code | KD-13,KD-18..21 | Not Started |  | —
KD-23 | 1 | Market data fetcher | yfinance → market_daily NIFTY + BANKNIFTY | Claude Code | KD-14,KD-17 | Not Started |  | —
KD-24 | 1 | Pipeline validation | 40yr data loaded. Risk ↔ volatility correlation verified. | Manual | KD-18..23 | Not Started | CRITICAL: product credibility depends on this | —
PHASE 2: SKILLS + SHELL (After framework ready)
KD-25 | 2 | GitHub repo from template | Create kaaladristi/ from vani-product-template | Manual | F-All,KD-01..15 | Not Started |  | —
KD-26 | 2 | risk-score-skill functions | get-risk-today, get-risk-by-date, get-risk-breakdown | Claude Code | KD-02,F-11 | Not Started |  | —
KD-27 | 2 | calendar-skill functions | get-calendar-7day, get-calendar-30day. Date-range queries. | Claude Code | KD-03 | Not Started |  | —
KD-28 | 2 | planetary-skill functions | get-positions-today, get-aspects-today, get-events-upcoming | Claude Code | KD-04 | Not Started |  | —
KD-29 | 2 | market-data-skill functions | get-market-today, get-market-history, get-correlation | Claude Code | KD-05 | Not Started |  | —
KD-30 | 2 | explanation-skill functions | explain-risk, explain-regime. Template NL or LFM2. | Claude Code | KD-06 | Not Started |  | —
KD-31 | 2 | Render: risk-dashboard | Hero risk gauge + regime + 7-day strip + explanation | Claude Code | KD-07 | Not Started | Primary screen | —
KD-32 | 2 | Render: calendar-view | 30-day grid, color-coded days, tap for detail | Claude Code | KD-08 | Not Started |  | —
KD-33 | 2 | Render: historical-overlay | Dual-axis: risk score line + market price line | Claude Code | KD-09 | Not Started |  | —
KD-34 | 2 | Auth + onboarding | Supabase auth. Trading style, risk appetite selection. | Claude Code | KD-16 | Not Started |  | —
KD-35 | 2 | WhatsApp alerts | Daily morning risk score push | Claude Code | - | Not Started | Post-MVP but high value | —
KD-36 | 2 | API endpoints | REST: /api/risk/today, /api/risk/calendar, /api/planets/today | Claude Code | KD-26..29 | Not Started |  | —
PHASE 3: VALIDATION + LAUNCH
KD-37 | 3 | Backtest validation | Overlay risk scores on historical market data | Manual | KD-24 | Not Started | Critical for product credibility | —
KD-38 | 3 | Weight tuning | Admin: adjust risk dimension weights. Preview on historical. | Claude Code | KD-37 | Not Started | IP-protected sliders | —
KD-39 | 3 | SEBI compliance review | Disclaimer on all screens. No buy/sell language. | Manual | - | Not Started |  | —
KD-40 | 3 | Beta launch | 10-20 traders. Feedback on risk score usefulness. | Manual | All | Not Started |  | —

## Summary
VaNi Product Framework — POA Status (Updated 2026-03-21)
Track | Total | Done | Partial | Bug | Not Started | % Complete
Framework Template | 52 | 36 | 5 | 4 | 7 | 74%
KI-Prime | 55 | 25 | 9 | 0 | 21 | 54%
KaalaDristi | 40 | 0 | 3 | 0 | 37 | 4%
TOTAL | 147 | 61 | 17 | 4 | 65 | 47%
KEY INSIGHTS
1. MILESTONE: End-to-end data flow proven — POST /api/v1/skills/client-skill/get_clients returns real data from Supabase.
2. FRAMEWORK: Phase 1 (backend) ~90% complete. Phase 2 (shell) components built but data fetching NOT wired.
3. KI-PRIME: 5 of 8 skills have handlers built. Only client-skill verified live. Others need ki_ prefix fix + testing.
4. KAALADRISTI: Effectively at 0% on VaNi framework. Ephemeris data generated in standalone Python. Not integrated.
5. CRITICAL BLOCKERS: 4 bugs (executor success field, toPositional regex, ki_ prefix, planning_math export) must be fixed before any further skill testing.
6. NEXT PRIORITY: Fix bugs → test remaining 4 skills → wire shell data fetching → first fully rendered recipe page.
7. ARCHITECTURE LESSON: Supabase transaction pooler set_tenant_context() doesn't persist — RLS strategy needs rethinking.
8. POA DELTA: Original POA showed 100% "Not Started". Reality: Framework ~65% done, KI-Prime ~45% done, KaalaDristi ~5% done.
RECOMMENDED NEXT STEPS (Priority Order)
1. Fix BUG-01 to BUG-04 (executor.ts, toPositional, ki_ prefix, planning_math) — unblocks all skill testing
2. Test portfolio-skill, market-skill, planning-skill, import-skill via Postman — validate data correctness
3. Wire shell recipe data fetching (KI-32) — first rendered recipe page with real data
4. Build alert-skill + report-skill handlers (Wave 5) — needed for daily-briefing recipe
5. Re-enable RLS with pooler-compatible strategy — critical for multi-tenancy security
6. Start KaalaDristi Phase 0 specs (KD-01 through KD-15) — can run parallel to KI-Prime Waves 4-5
7. Docker Compose for dev environment (F-43 through F-46) — standardize developer setup