VIKUNA TECHNOLOGIES

VaNi AI — Plan of Action

Execution Guide for Claude Code

Workstreams, Tasks, Owners, Gates & Sequencing

Companion to: App Spec v1 + Addendum A · Mentor Brief · UX Blueprint v1 · Pilot Pack v1

Version 1.0  |  31 July 2026  |  Working Document

Author: Charan Kamal Bommakanti, Founder & CEO

Confidential — Vikuna Technologies

# POA Overview

This POA takes VaNi AI from documents to a live, lead-generating assessment platform at vani.vikuna.io in four weeks. Seven workstreams, three owners, five approval gates. Claude Code (the website session) is the primary builder; the Cowork session designs and reviews; Charan owns infrastructure access, approvals and launch.

## Reading Order for Claude Code

- 1. VaNi_AI_App_Spec_v1.docx — the contract (§4 partially superseded by Addendum A).

- 2. VANI_AI_MENTOR_BRIEF.md incl. Addendum A — guardrails, vani_gtm directive, Supabase prohibition.

- 3. vani-ai-ux-blueprint.html — the design system. Implement it, do not reinterpret it. The CSS custom properties are the tokens.

- 4. AI_Failed_Initiatives_Audit_PilotPack_v1.docx §3 — the survey instrument to seed verbatim.

- 5. This POA — what to do, in what order, and where the gates are.

## Workstream Summary

| WS | Workstream | Owner | Phase | Priority |
| --- | --- | --- | --- | --- |
| 0 | Infrastructure Prerequisites | Charan (+ Claude Code assist) | A | Critical |
| 1 | Design Blueprint Completion | Cowork session | A | Critical |
| 2 | Data Layer & Scoring (vani_gtm) | Claude Code | A | Critical |
| 3 | Public Assessment App | Claude Code | B | Critical |
| 4 | Report Pipeline & Email | Claude Code (+ N8N/worker) | B | High |
| 5 | Console (Owner + Partner) | Claude Code | C | High |
| 6 | Launch, Content & First Prospects | Charan (+ Cowork session) | D | High |

## Phase Timeline & Gates

| Phase | Window | Focus | Gate at Exit |
| --- | --- | --- | --- |
| A | Aug 3–9 | Prereqs answered & done; design complete; migrations written and reviewed | G1 — Charan approves schema + blocking answers resolved |
| B | Aug 10–16 | Public flow live on preview; pipeline delivers report email | G2 — phone demo end-to-end · G3 — email lands in inbox, not spam |
| C | Aug 17–23 | Console with roles; partner isolation proven | G4 — partner cannot see another partner’s leads (test shown) |
| D | Aug 24–31 | Dry run, friendly prospects, content, DNS to production | G5 — Charan launches publicly |

# WS0 — Infrastructure Prerequisites (Charan)

Everything here blocks P1 builds. Most items are under 30 minutes each. Claude Code may assist via SSH tasks where Charan grants access.

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 0.1 | Answer Addendum A blocking questions: where vani_gtm runs; is the GTM event bus + worker deployed against it; what serves it over HTTP | Written answers to Claude Code + Cowork session | Critical |
| 0.2 | DNS: create vani.vikuna.io (and api.vikuna.io if Option A) A-records → Main VPS | Resolving subdomains | Critical |
| 0.3 | Let’s Encrypt on Main VPS Nginx (already on infra checklist); certs for the new hosts | HTTPS live | Critical |
| 0.4 | PostgREST instance pointed at vani_gtm (new container if needed), CORS for Vercel origins | API base URL | Critical |
| 0.5 | HostingRaja SMTP credentials into N8N/worker env; verify SPF/DKIM for vikuna.io senders | Test email passes to Gmail + Outlook inboxes | High |
| 0.6 | Add swap to Main VPS (flagged zero-swap risk); confirm RAM headroom | Swap active | Medium |
| 0.7 | Booking link for L2 scoping call (Calendly/Zoho Bookings or equivalent) for the report CTA | Working booking URL | Medium |

# WS1 — Design Blueprint Completion (Cowork Session)

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 1.1 | Console screens in blueprint: login, leads list (filters, columns per spec §3.4), lead detail (answers, mode chart, pipeline, notes, resend), partner links view | Blueprint v2 (same HTML file, extended) | Critical |
| 1.2 | Report-delivery email template — light, minimal, table-based HTML that renders in Outlook/Gmail; plain-text alternative | email-report.html + .txt in blueprint pack | Critical |
| 1.3 | Edge states: invalid/expired report token page; resume-in-progress prompt; generic error | Added to blueprint v2 | High |
| 1.4 | Handoff notes: component inventory + token table for Claude Code | One-page addendum in the blueprint file header | Medium |

# WS2 — Data Layer & Scoring (Claude Code · Phase A)

Protocol Inspect the live vani_gtm schema FIRST and align names with existing gt_ conventions before creating anything. Migrations are written as reviewable SQL files and applied only after Gate G1. Nothing touches Supabase.

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 2.1 | Schema inspection report: existing gt_ tables, tenant model, event bus tables, how Vikuna Consulting becomes tenant #1 | Short written report → G1 input | Critical |
| 2.2 | Migrations: gt_assessment_def, gt_assessment_response, gt_assessment_report, prospect staging row for leads, partner users, lead events — tenant-scoped, RLS on all | SQL migration files | Critical |
| 2.3 | Scoring function (SQL): answers × def weights → mode exposures, health score, band (71/41 thresholds) | vn/gt scoring fn + unit tests | Critical |
| 2.4 | Login RPC (pgjwt) issuing role + partner claims; PostgREST role grants (anon / partner / owner) | Auth working via PostgREST | Critical |
| 2.5 | Seed ai-recovery definition verbatim from Pilot Pack §3 (12 questions, weights, bands, framing + teaser copy) | Seeded row; scoring dry-run passes | Critical |

# WS3 — Public Assessment App (Claude Code · Phase B)

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 3.1 | Implement blueprint screens 1–5 (landing, assessment, analyzing, teaser, capture) in the website project per the Option A/B decision; config-driven from gt_assessment_def | Preview URL | Critical |
| 3.2 | Response row on first answer (anon token); ref= partner attribution captured; back navigation; resume state | Verified against spec §3.2 | Critical |
| 3.3 | Report page /r/{token} from blueprint report design; print CSS; invalid-token state | Live tokenized report | Critical |
| 3.4 | Mobile & performance pass: 390px, <1s first load on 4G, no heavy libraries on public path | Lighthouse/notes → G2 | High |

# WS4 — Report Pipeline & Email (Claude Code · Phase B)

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 4.1 | Orchestration per 0.1 answer: ASSESSMENT_COMPLETED event + registered report agent (preferred) OR N8N flow F1 | Working pipeline | Critical |
| 4.2 | Qwen3 narrative generation (/no_think, internal endpoint) from computed scores + approved mode copy; template fallback on any failure | Narrative in report; fallback tested | High |
| 4.3 | Email delivery via HostingRaja SMTP using WS1.2 template; owner notification on each new lead | G3 evidence: inbox screenshots | Critical |
| 4.4 | Daily owner digest (08:00 IST) + 3-day stale-lead nudge | Scheduled flows | Medium |

# WS5 — Console (Claude Code · Phase C)

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 5.1 | Login + session handling on the pgjwt RPC; owner and partner roles | Working login | Critical |
| 5.2 | Leads list + lead detail + pipeline statuses + notes + resend, per blueprint v2 | Console live on preview | Critical |
| 5.3 | RLS isolation test: two partner accounts, cross-visibility proven impossible; test kept in repo | G4 evidence | Critical |
| 5.4 | Partner links view; abandoned-responses view; hold_for_review flag honored | Complete console v1 | High |

# WS6 — Launch, Content & First Prospects (Charan · Phase D)

| # | Task | Output | Priority |
| --- | --- | --- | --- |
| 6.1 | Dry run: fictional client end-to-end; Charan reviews report quality and VaNi voice | Sign-off or revision list | Critical |
| 6.2 | 3–5 friendly prospects through the live flow; iterate wording/scoring from real reactions | Calibrated v1.1 definition | Critical |
| 6.3 | One-pager (Pilot Pack §7.1) + LinkedIn failure-mode series posts 1–3 scheduled | Collateral live | High |
| 6.4 | Onboard first partner: account, tagged links, 15-minute walkthrough | First attributed lead path | High |
| 6.5 | Public launch: link from vikuna.io, LinkedIn announcement, survey CTA in email signatures | Launched | High |

# Claude Code Session Protocol

- One phase per session, gates are hard. Do not begin a workstream whose gate dependency has not been approved by Charan. Demonstrate exit criteria, then stop.

- Report before building. Phase A starts with the Part 1 website-state answers (Mentor Brief) + the 2.1 schema inspection + the Option A/B proposal — all before any code.

- The blueprint is law. Pixel-level fidelity to vani-ai-ux-blueprint.html; its CSS custom properties are the design tokens. No substitute component libraries on the public path.

- The ten guardrails of the Mentor Brief apply throughout — especially: no Supabase for VaNi AI data, no new auth services, config-driven survey engine, deterministic SQL scoring, secrets never in the Vercel project.

- Escalation path. Ambiguity or conflict between documents → flag to Charan, who relays to the Cowork session. Precedence: this POA > Addendum A > App Spec > Mentor Brief body > Blueprint (for anything non-visual).

- Do not touch the ContractNest–Supabase coupling, existing website routes beyond what integration requires, or any DristiQ/KI-Prime infrastructure.

# Immediate Next Steps (This Week)

| # | Action | Owner | Status |
| --- | --- | --- | --- |
| 1 | Approve this POA | Charan | Pending |
| 2 | WS0.1 answers (vani_gtm location, event bus, HTTP layer) + WS0.2 DNS | Charan | Start now |
| 3 | WS1.1–1.3: extend blueprint with console, email template, edge states | Cowork session | On approval |
| 4 | Share spec + brief + blueprint + POA with Claude Code; it returns Part 1 answers + 2.1 schema report + Option A/B proposal | Charan → Claude Code | Start now |
| 5 | Gate G1 review of schema + migrations | Charan + Cowork session | After 2–4 |